## Zone
SIRA Location | Name of location | Zone number | 1 | [15 empty] | SIRA Workbook |  | V2.0
Defining the undesired scenario |  |  |  | What kind of consequences could occur? | Why could it happen or why did it happen? | What usually stops it happening? | What is the level of risk now? How likely will the undesired scenario occur and what will the likely |  |  |  |  | What could reduce the level of risk? | What would the level of risk be with the new control measures? |  |  |  | How much will the control measures cost over their lifetime?
Hazard | Type of scenario | Description of scenario/incident | Zone/ Hazard/ Scenario Ref. | Consequences | Root cause(s) | Existing risk control measures | Likelihood Score 1-5 | Reasoning behind Likelihood Score | Impact Score 1-5 | Reasoning behind Impact score (Short term and long term) | Initial risk score | Further risk control options that could reduce either Liikelihood or Impact | Revised Likelihood Score 1-5 | Revised Impact Score 1-5 | Residual risk score | Change in risk score | Initial cost (e.g., design, purchase, installation, commission) | Anticpated lifetime of control measure in years | Average annual cost (e.g., maintenance, operation, monitoring) | Estimated whole life cost | Cumulative estimated whole life cost
Reef at Prince William Sound | Grounding | Oil tanker grounds on reef | 1.1.1 | Significant oil spillage resulting in lost cargo, environmental damage, oil spill clean up and legal action | Inadequate VTS communications infrastructure. Lack of spatial awareness, especially at night Vessel speed. Vessel transit routes Lack of crew adherence to working practices Lack of available crew | VTS with warning protocols Traffic lanes Competent crews | 2 | Historically has only occurred once but is not rare because it is a common transit area for oil tankers. In normal conditions without icebergs transiting is within normal traffic lanes. | 5 | Devastating environmental effect of historical incident costing $2 million clean up and $3 million lost product. | 10 | Add additional radar sites ($3.3 million) | 1 | 5 | 5 | 5 | 3000000 | 30 | 10000 | 3300000 | 3300000
Reef at Prince William Sound | Grounding | Oil tanker grounds on reef | 1.1.1 | As for Scenario 1 | As for Scenario 1 | As for Scenario 1 | 2 | As for Scenario 1 | 5 | As for Scenario 1 | 10 | Amend warning procedures ($1000) | 1 | 5 | 5 | 5 | 1000 | 30 | 0 | 1000 | 3301000
Reef at Prince William Sound | Grounding | Oil tanker grounds on reef | 1.1.1 | As for Scenario 1 | As for Scenario 1 | As for Scenario 1 | 2 | As for Scenario 2 | 5 | As for Scenario 1 | 10 | Modify traffic routes ($30,000 consultation, IMO liaison, mapping) | 1 | 5 | 5 | 5 | 30000 | 30 | 0 | 30000 | 3331000
Reef at Prince William Sound | Grounding | Oil tanker grounds on reef | 1.1.1 | As for Scenario 1 | As for Scenario 1 | As for Scenario 1 | 2 | As for Scenario 3 | 5 | As for Scenario 1 | 10 | Apply speed limit in the sound ($5000, new documentation) | 1 | 5 | 5 | 5 | 5000 | 30 | 0 | 5000 | 3336000
Reef at Prince William Sound | Grounding | Oil tanker grounds on reef | 1.1.1 | As for Scenario 1 | As for Scenario 1 | As for Scenario 1 | 2 | As for Scenario 4 | 5 | As for Scenario 1 | 10 | Apply daytime transit to the sound ($10,000 documentaion and liaison) | 1 | 5 | 5 | 5 | 10000 | 30 | 0 | 10000 | 3346000
These must link
Note on B5: General grouping of scenario type based on G1138 Annex B
Note on D5: Unique reference to refer to in report e.g. zone 1, hazard 1, scenario 1 could be 1.1.1
Note on F5: e.g., use "Five Whys" to understand root cause and any contributory causes
Note on A6: Insert rows as necessary for number of scenarios

## Dropdowns
Grounding | 1
Allision | 2
Collision | 3
Foundering | 4
Strucural failure | 5
Other